## Sheet1
Aglie Practical Project
Company Name
Project Lead
Project Start Date: | 14/2/2022 |  |  |  |  | February | [14 empty] | March | [30 empty] | April | [29 empty] | May
[6 empty] | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 29 | 30 | 31 | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 29 | 30 | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 29 | 30 | 31
Milstone Desciption | Category | Assigned to | Progress | Start | Days | M | T | W | T | F | S | S | M | T | W | T | F | S | S | M | T | W | T | F | S | S | M | T | W | T | F | S | S | M | T | W | T | F | S | S | M | T | W | T | F | S | S | M | T | W | T | F | S | S | M | T | W | T | F | S | S | M | T | W | T | F | S | S | M | T | W | T | F | S | S | M | T | W | T | F | S | S | M | T | W | T | F | S | S | M | T | W | T | F | S | S | M | T | W | T | F | S | S | M | T | W | T | F | S | S | M | T
Iteration 1
Group Meeting Report | Low Risk | Joost | 100% | 15/2/2022 | 1 | bar: February 15 T
Complete Stakeholder Register | Med Risk | Jordyn | 100% | 15/2/2022 | 14 | bar: February 15 T to February 28 M
Create Personas | Med Risk | Jordy and Alex | 100% | 2022-01-03 | 7 | bar: March 1 T to March 7 M
Review Personas | High Risk | Joost | 100% | 2022-08-03 | 7 | bar: March 8 T to March 14 M
Milestone | Milestone |  | 100% | 15/3/2022 | 1 | bar: March 15 T
Iteration 2
Group Meeting Report | Low Risk | Joost | 100% | 15/3/2022 | 1 | bar: March 15 T
Create Gantt Chart | Med Risk | Alex | 100% | 15/3/2022 | 14 | bar: March 15 T to March 28 M
Assign Task based on Stakeholder Register | High Risk | Joost | 100% | 22/3/2022 | 14 | bar: March 22 T to April 4 M
Create a Resource Requiremnt List | High Risk | Jordyn | 100% | 2022-05-04 | 7 | bar: April 5 T to April 12 T
Milestone | Milestone |  | 100% | 2022-12-04 | 1 | April 12 T: 2
Iteration 3
Group Meeting Report | Low Risk | Joost | 100% | 2022-03-05 | 1 | bar: May 3 T
Create Risk Register | High Risk | Jordyn | 100% | 2022-03-05 | 7 | bar: May 3 T to May 9 M
Push, Merge and Publish Webiste | High Risk | Jordyn, Joost and Alex | 100% | 2022-10-05 | 14 | bar: May 10 T to May 23 M
Complete User Acceptance Test | Med Risk | Alex | 100% | 24/5/2022 | 7 | bar: May 24 T to May 30 M
Milestone | Milestone |  | 100% | 31/5/2022 | 1 | May 31 T: 3