## Sheet1
27/05/2022 | 16:00 | Who: Alex Borawski | Application: Timups
ID | Scenario Title | Status | Scenario | Remarks
1 | Scrolling Through the Homepage | Pass | Page loaded and be able to be scrolled thorught to show all information on the page | The banner at the top of the page showed the same information on all 3 pages but otherwise good
2 | Get into a individual watch page | Failed | When on the main page or watches page, you can get into the indivdual page about a single watch | When you click on an individual watch, it links back to the main page
3 | Send a contact message | Pass | On the homepage, send a message to the creators | This worked well, even required us to have proper email format, but there was no confirmation to the user that it was sent
4 | Find out more info abou the watch products | Failed | Find out more about the features our watches have. | Same as scenario 2, the links just send you to the top of the home page
5 | See our social network pages | Failed | Get to our social media accounts from the home page | These link do not appear to be working, and jsut appears to refresh the page
6 | Read customer Testimonials | Pass | Read some of our customers testimonials on out home page | Simple and easy to do, just at the bottom of the page. Would consider removing the arrow if their are only two.
7 | View all of our watches | Failed | See all of our available watches on the Watches page | Although there appeared to be all of the available watches visable on the page, the "View all" button confused me when it just reloaded the page
8 | See you previous order(s) | Pass | Go see any previous orders you have made with us in the Order page | Clearly displayed any orders the user would have made, as well as all revelant information
9 | Track you order | Failed | Try and track your order to see where it currently is in the delivery process | This link also seemed to be broken and not do anything when I interacted with it
10 | Request a return | Failed | Try to return one of the products that have been ordered | Again, this didnt appear to do anything. If was meant to email a return form to the user, there was no visual indication of that happening